## Development Gates SS28
DEVELOPMENT GATES SS28 SPW |  |  |  |  | APACHE內部工作事項 |  | TT | T2
Apache India • Asia / India working cadence |  |  |  |  | MODEL: NSS73, NSS74, NSS75, NSS76
PjM: Marketing Godfrey, Mark; Designer and Tooling tech: Park, Patrick |  |  |  |  | ARTICLES: LN5327, LN5332, LN5337, LN5346
DATE 日期 | GATE 進度 | EXPECTED OUTPUT 預期結果 | OWNERSHIP / LOCATION 負責人及地點 | STATUS 行動 | APC | WANG-YU | Team Travel | BOOST
W/O 24 AUG (08月24日) | Tech-Pack handover 技術包裹轉移 | Complete Tech-Pack handed over 完成技術包裹轉移 | Asia → India (Online) 亞洲 > 印度 (線上會議) | HANDOVER 轉移 | 1. 8月27日技術包裹轉移會議 2. 同步提供TP到萬裕 | 1. 08月29日初版2D； 2. 09月02日初版3D； 3. 客人改完初版後製作快模 | Shell pattern, Material map, CAD, Reference design, Artwork, O/S#, Last#21098 #21096
07 SEP (09月07日) | 1st Pullover + tooling 2D 第一輪試版+底模2D | First physical pullover + 2D review 第一輪實際試版+底模2D瀏覽 | India team presents in Vietnam 印度團隊出席越南 (實體會議) | VN REVIEW 越南 | 09月05日清奈出發>06日抵達胡志明; (5名)CLAIRE, NEIL | 攜帶底模快模; 1名(2D)出發 | Thread, Upper material, Reinforcement, Treatment Component, Heel counter, Lace, Socklinear, Insole, Foam, Hangtag(Grey), Fast O/S, Last
14 SEP (09月14日) | 2nd Round Pullover 第二輪試版 | Updated sample / construction / 2D / 3D review 更新樣品/結構/2D/3D瀏覽 | India team presents in Vietnam 印度團隊出席越南 (實體會議) | VN REVIEW 越南 | CATHERINE, NEIL
21 SEP (09月21日) | 3rd Pullover / CR0 Sample + Costing 第三輪試版+CR0樣品+報價 | CR0 sample + tooling RP + costing; acts as CR0 MST sample CR0樣品+快模+報價；CR0 MST(面料採購團隊)樣品 | India team presents in Vietnam 印度團隊出席越南 (實體會議) | VN REVIEW 越南 | ZANE, CHANDU, HELEN
30 SEP–02 OCT (09月30日-10月02日) | CR0 / MST Internal Review CR0/MST (面料採購團隊)內部瀏覽 | Internal assessment and consolidated revision direction 內部評估與綜合修正方向 | Adidas internal only 品牌內部會議 | INTERNAL REVIEW 內部會議
07 OCT (10月07日) | CR0 / MST Revisions CR0/MST (面料採購團隊)修正 | Revision package handover 修正技術包裹轉移 | Asia → India (Online) 亞洲 > 印度 (線上會議) | HANDOVER 轉移
09 OCT (10月09日) | CR1 Color & Material MAPs CR1顏色與材料校對 | CR1 colors and material MAPs issued to T1 CR1顏色與材料校對提供至工廠端 | Asia → India (Online) 亞洲 > 印度 (線上會議) | HANDOVER 轉移
14 OCT (10月14日) | 4th Pullover 第四輪試版 | Updated pullover / 2D / 3D review 更新樣品/2D/3D瀏覽 | India team presents in Vietnam 印度團隊出席越南 (實體會議) | VN REVIEW 越南 | 10月12日清奈出發>21日 | CR0真模>底部樣品 預計2名(2D+3D)出發
16 OCT (10月16日) | Tooling confirmation 底模確認 | 2D/3D Tooling sign-off for CR1 mold opening CR1底模開制: 2D/3D簽准 | Asia + India via e-mail / Teams 亞洲+印度郵件與線上溝通 | SIGN-OFF 簽准 | 套楦鞋面: RAPIDFIT + SOCK CR1不須FIT/WEAR 5T+8T看木模 厚度看RAPIDFIT來量模口 | CR1初模確認開製 YEE-FENG提供材料
21 OCT (10月21日) | 5th Pullover 第五輪試版 | Updated pullover, upper sign-off for CR1. 更新樣品，CR1鞋面簽准 | India team presents in Vietnam 印度團隊出席越南 (實體會議) | VN REVIEW 越南
13 NOV (11月13日) | CR1 Final samples XFAC CR1最終樣品出廠 | Final samples, all colorways & full costing CR1階段最終樣品/配色/報價 | India ship full quantities to Vietnam and HQ | CR1 XFAC CR1樣品出廠 |  | CR1底部樣品寄給APC
23-27 NOV (11月23-27日) | CR1 / TT Internal Review TEAM TRAVEL瀏覽CR1樣品 | Internal assessment and consolidated revision direction 內部評估與綜合修正方向 | Adidas internal only 品牌內部會議 | INTERNAL REVIEW 內部會議
2 DEC (12月02日) | CR1 Revisions CR1修正 | Revision package handover 修正技術包裹轉移 | Asia → India (Online) 亞洲 > 印度 (線上會議) | HANDOVER 轉移
4 DEC (12月04日) | Revisions to color & materials for CR2 修正顏色與材料: 供CR2階段 | Revisions to colors and materials for CR2 修正顏色與材料: 供CR2階段 | Asia → India (Online) 亞洲 > 印度 (線上會議) | HANDOVER 轉移
9 DEC (12月09日) | 6th Pullover 第六輪試版 | Updated pullover / 2D / 3D review 更新樣品/2D/3D瀏覽 | India team presents in Vietnam 印度團隊出席越南 (實體會議) | VN REVIEW 越南 | 12月07日清奈出發>17日 | CR1真模>底部樣品 預計2名(2D+3D)出發
11 DEC (12月11日) | Tooling confirmation 底模確認 | 2D/3D Tooling sign-off for CR2 mold opening CR2底模開制: 2D/3D簽准 | Asia + India via e-mail / Teams 亞洲+印度郵件與線上溝通 | SIGN-OFF 簽准 |  | CR2真模確認開製
16 DEC (12月16日) | 7th Pullover (if required) 第七輪試版 | Updated pullover, upper sign-off for CR2. Final costing check. 更新樣品，CR2鞋面簽准，最終報價確認 | India team presents in Vietnam 印度團隊出席越南 (實體會議) | VN REVIEW 越南
27 JAN (01月27日) | CR2 Final samples XFAC CR2最終樣品出廠 | Final samples, all colorways ( & costing by 28th ) CR2階段最終樣品/配色/報價-01月28日提供 | India ship to Asia and Markets 印度寄出至亞洲/MKT | CR2 XFAC CR2樣品出廠 |  | CR2底部樣品寄給APC

## SS28 SPW TN Calendar
Product Group (M) | AGE GROUPING | Corporate Marketing Line (M) | Gender (M) | Development Type (M) | Model Name [Short] (M) | Age Group (M) | Model Number (M) | Product Manager (M) | Model Status (M) | Marketing Forecast (M) | Reference Model Number (M) | Outsole Number (M) | Target Material (M) | Technology Concept (M) | Sales Line (M) | Project Calender | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
SHOES | ADULT | LIFESTYLE RUNNING | MALE | TOTALLY NEW | BOOST CUXXION - RAPIDFIT | ADULT | NSS73 | William Hester | RELEASED | 80000 |  | 98345 | TEXTILE | BOOST+ | WALKING RANGE | Week1 Target | 1. Mater Pattern ¦ 2. 1st-Stitched Upper Ready ¦ 3. 1st-File 2D/3D Ready ¦ 4. Stitched Upper 1st-Costing Review/w BU
SHOES | ADULT | LIFESTYLE RUNNING | FEMALE | NEW SILHOUETTE | BOOST CUXXION - RAPIDFIT | ADULT | NSS74 | William Hester | RELEASED | 70000 |  | 98348 | TEXTILE | BOOST+ | WALKING RANGE | Date | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29
SHOES | ADULT | LIFESTYLE RUNNING | MALE | NEW SILHOUETTE | BOOST CUXXION - SOCK | ADULT | NSS75 | William Hester | RELEASED | 75000 |  | 98345 | TEXTILE | BOOST+ | WALKING RANGE | Daily Target |  |  |  | 1. BU SPW TPHO Meeting 2. Internal TP Meeting | 1. SPEC (Excel) morning 10:00 2. CR0 Material - purchase order 3. Material Sub - list out 4. Stock Sub - list out 5. Lamination Matl. - list out | 1. Master Pattern morning 10:00 2. 2D 1st-File receive
SHOES | ADULT | LIFESTYLE RUNNING | FEMALE | TAKE DOWN | BOOST CUXXION - SOCK | ADULT | NSS76 | William Hester | RELEASED | 75000 |  | 98348 | TEXTILE | BOOST+ | WALKING RANGE | 1H Target |  |  |  | Ext. & Int. Meeting | 1. SPEC (Excel) morning 10:00 2. CR0 Material - purchase order 3. Material Sub - list out 4. Stock Sub - list out 5. Lamination Matl. - list out | 1. Master Pattern morning 10:00 2. 2D 1st-File receive
[16 empty] | 2H Target | [5 empty] | 1. Review Stock Sub Matl. 2. Cutting 3. Lamination matl. Changed
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
[16 empty] | Bottom Mold | -
[16 empty] | Remark | BU SPW, TPHO/W | BU SPW, TPHO/W | BU SPW, TPHO/W | BU SPW, TPHO/W 1. Day 0 = TP Receiving | BU SPW, TPHO/W 1. Day 1 = TP Received | BU SPW, TPHO/W 1. Day 2 = TP Received
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
[16 empty] | Week2 Target | 1ST 2D-File ¦ 1ST Pullover Finalize/w Treatment ¦ Ready to TT
[16 empty] | Date | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05
[16 empty] | Daily Target | 1. 2D 1ST-FILE REVIEW/W BU 2. 2D 1ST-FILE AMEND | Review 1ST pullover | Review 1ST-Amend pullover | Finalize 1ST pullover | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Remind WangYu attandence | 1. CR0 TT Departure=1ST-Round 2. Claire+Neil+WangYu 3. 1ST-Round=First physical pullover + 2D review
[16 empty] | 1H Target | 1. Review stock matl. Lamination status 2. Correct matl. Check with APH W/H 3. Cutting starts | 1. First pullover review 2. Pattern modification | 1. Amended pullover review 2. Pattern modification 3. Amend. Pullover/w treatment | 1. Rapidfit and Sock version review | 1. 3D 1ST-FILE 2. 3D 1ST-FILE REVIEW/W BU | 1. WOODEN MOLD
[16 empty] | 2H Target | 4. Stitching starts | 3. Another pullover starts | 3. Finalize First round pullover | 2. Prepare matl. Hard-copy files
[16 empty] | Upper Pattern | H/O 1ST P/O version | Amend after 1ST P/O | Finalize for 1ST P/O | 1ST P/O minor amend | 1. Finalize Pattern for 1ST CR0 TT 2. Share the pattern file with APH to print-out
Upper Mold
[16 empty] | Material WH | H/O Sub/Stock matl. | Amend after 1ST P/O | Finalize for 1ST P/O | H/O 1ST P/O Sub/Stock matl.
[16 empty] | Lamination | H/O Sub/Stock matl. | Amend after 1ST P/O | Finalize for 1ST P/O | H/O 1ST P/O Sub/Stock matl.
[16 empty] | Cutting | Starting 1ST P/O | Starting 1ST-Amend P/O | Finalize for 1ST P/O | Await for fianl touch
[16 empty] | Treatment |  | Adding 1ST P/O | Finalize for 1ST P/O | Await for fianl touch
[16 empty] | Stitching | Starting 1ST P/O | Starting 1ST-Amend P/O | Finalize for 1ST P/O | Await for fianl touch
[16 empty] | Costing |  | SOCK: $13.44 | Review RF model | Review 1ST P/O CBD | Final CBD for both model
[16 empty] | Bottom 2D/3D | Ready in 2D-file | Ready in 2D-file | Scan lasted upper for 3D | Review 1ST 2D-file/w BU
Bottom Mold
[16 empty] | Remark | 1. Day 3 = TP Received | 1. Day 4 = TP Received | 1. Day 5 = TP Received | 1. Day 6 = TP Received | 1. Day 7 = TP Received 2. Leaving dorm in the evening | 1. Day 8 = TP Received 2. 1ST-Round P/O
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week3 Target
[16 empty] | Date | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12
[16 empty] | Daily Target | CR0 TT 1ST Review 2D+PULLOVER | CR0 TT | 1. CR0 TT 2. CR0 TT Return 3. 2ND pullover Ready | Finalize 2ND pullover | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Remind WangYu attandence | 1. CR0 TT Departure=2ND-Round 2. Catherine+Neil+WangYu 3. 2ND-Round=Updated sample / construction / 2D / 3D review
[16 empty] | 1H Target | 1. Con. Call /w APC Team | 1. 2ND pullover matl. Ready 2. 2ND pattern Ready | 1. Review 2ND pullover 2. Impro. 2ND pullover | 1. 1ST 2D file adj. 2. 1ST 3D file start | 1. 1ST 3D file receive and share/w BU
[16 empty] | 2H Target | 2. 1ST pullover Feedback Recap 3. 1ST pattern Feedback adjust | 3. 2ND pullover cutting & stitching | 3. Finalize 2ND pullover | 1. Rapidfit and Sock version review 2. Prepare matl. Hard-copy files
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
[16 empty] | Bottom 2D/3D |  | Adv. Check for 2D+3D | Adv. Review for 2D+3D/w BU
Bottom Mold
[16 empty] | Remark | 1. APC review Pullover online/w BU | 1. APC review Pullover online/w BU |  | 1. Jervis vacation | 1. Jervis vacation | 1. 2ND-Round P/O 2. Jervis vacation
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week4 Target
[16 empty] | Date | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19
[16 empty] | Daily Target | CR0 TT 2ND Review CONFIRM 2D+3D | CR0 2ND TT | 1. CR0 2ND TT 2. CR0 2ND TT Return |  | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Remind WangYu attandence | 1. CR0 TT Departure=3RD-Round 2. Catherine+Helen+WangYu 3. 3RD-Round=CR0 sample + tooling RP + costing; acts as CR0 MST sample CR0
[16 empty] | 1H Target | 1. Con. Call /w APC Team | 1. 3RD pullover matl. Ready (BU requested matl.) 2. 3RD pattern Ready | 1. Review 3RD pullover 2. Impro. 3RD pullover | 1. 2ND 2D file finish 2. 2ND 3D file finish 3. RP start | 1. 2ND 2D+3D file receive and share/w BU | 1. RP finish and hand-carry
[16 empty] | 2H Target | 2. 2ND pullover Feedback Recap 3. 2ND pattern Feedback adjust | 3. 3RD pullover cutting & stitching | 3. Finalize 3RD pullover
Upper Pattern
Upper Mold
[16 empty] | Material WH |  | Lastest matl. ETA
Lamination
Cutting
Treatment
Stitching
Costing
[16 empty] | Bottom 2D/3D |  | Adv. Check for 2D+3D/w WangYu | Adv. Review for 2D+3D/w WangYu | Pre. For RP LT 3-day | Pre. For RP LT 3-day | Pre. For RP LT 3-day
Bottom Mold
[16 empty] | Remark | 1. Jervis vacation | 1. Jervis vacation | 1. Jervis vacation | 1. Jervis vacation | 1. Jervis vacation | 1. 3RD-Round P/O 2. Jervis vacation
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week5 Target
[16 empty] | Date | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26
[16 empty] | Daily Target | CR0 TT 3RD Review CR0 sample + tooling RP + costing | CR0 TT 3RD Review | CR0 TT 3RD Return | CR0 TT feedback file org. CR0 TT internal review
[16 empty] | 1H Target | 1. Con. Call /w APC Team
[16 empty] | 2H Target | 2. 3RD pullover Feedback Recap 3. 3RD pattern Feedback adjust
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
[16 empty] | Bottom Mold |  |  |  | 1. Org.=Organize
[16 empty] | Remark | 1. Jervis vacation | 1. Jervis vacation | 1. Jervis vacation | 1. Zane vacation 2. Jervis vacation | 1. Zane vacation 2. Jervis vacation | 1. Zane vacation 2. Jervis vacation
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week6 Target
[16 empty] | Date | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
[16 empty] | Remark | 1. Zane vacation 2. Jervis vacation | 1. Zane vacation 2. Jervis vacation | 1. Zane vacation | 1. Catherine vacation 2. Zane vacation | 1. Catherine vacation 2. Zane vacation 3. Neil vacation | 1. Catherine vacation 2. Zane vacation 3. Neil vacation
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week7 Target
[16 empty] | Date | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10
[16 empty] | Daily Target |  |  | 1. Share revised TP 2. Review revised TP 3. 2D/3D 2nd revision | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 2nd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 2nd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 2nd Remind
[16 empty] | 1H Target |  |  | 1. Developer revise SPEC 2. PUR order new TP matl.
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
[16 empty] | Remark | 1. Catherine vacation 2. Zane vacation 3. Neil vacation | 1. Catherine vacation 2. Neil vacation | 1. Catherine vacation 2. Neil vacation | 1. Catherine vacation 2. Neil vacation | 1. Catherine vacation 2. Neil vacation | 1. Neil vacation
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week8 Target
[16 empty] | Date | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17
[16 empty] | Daily Target | CR1 4TH TT Dept. | CR1 4TH TT Arr. | 1. CR1 4TH TT Begin-day 2. CR1 2D/3D Sign-off 3. CR1 Tooling Confirmation | 1. CR1 TT 2. Stitched Upper Scan 3. Confirm M/S ETC 4. Confirm O/S ETC | 1. CR1 TT 2. Wooden Pattern ETC | 1. CR1 TT 2. Wooden Pattern ETC
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week9 Target
[16 empty] | Date | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24
[16 empty] | Daily Target | CR1 5TH TT Dept. | CR1 5TH TT Arr. | CR1 5TH TT Begin-day CR1 5TH pullover Sign-off | TT Return-Dept | TT Return-Arr | CR1 TT feedback file org. CR1 TT internal review
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week10 Target
[16 empty] | Date | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31
[16 empty] | Daily Target | [5 empty] | 1. China Mold Shop Trip 2. CR1 Molds ETC
[16 empty] | 1H Target | [5 empty] | 1. YEE-FENG TOOLING LT 2. TA ETC 3. BOOST M/S = PROD. TOOLING 60-DAY 4. RUBBER O/S = PROD. TOOLING 40-DAY
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week11 Target
[16 empty] | Date | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07
[16 empty] | Daily Target | 1. China Mold Shop Trip 2. CR1 Molds ETC | 1. China Mold Shop Trip 2. CR1 M/S Component 3. CR1 O/S Component | 1. Trip return-Dept 2. Component hang-carry | 1. Trip return-Arr 2. Component hang-carry | 1. CR1 Assembly 1st-trial | 1. CR1 1st-Sample review
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week12 Target
[16 empty] | Date | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14
[16 empty] | Daily Target | 1. CR1 Assembly 2nd-trial | 1. CR1 2nd-Sample review | CR1 Final Samples Review | CR1 Final Samples Review | CR1 Final Samples XFAC
1H Target
[16 empty] | 2H Target |  |  |  |  | Share CR1 AWB/w BU
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
[16 empty] | Remark | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week13 Target
[16 empty] | Date | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
[16 empty] | Remark | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation | 1. Helen vacation
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week14 Target
[16 empty] | Date | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week15 Target
[16 empty] | Date | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05
[16 empty] | Daily Target |  |  | 1. Share revised TP 2. Review revised TP 3. 2D/3D 3rd revision | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 3rd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 3rd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 3rd Remind
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week16 Target
[16 empty] | Date | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12
[16 empty] | Daily Target | TT Departure 1. GTM / Early Pre-sell Order | TT Arrival 1. GTM / Early Pre-sell Order | CR2 TT Start 1. GTM / Early Pre-sell Order | CR2 TT 1. GTM / Early Pre-sell Order | 1. GTM / Early Pre-sell Order | CR2 TT 1. GTM / Early Pre-sell Order
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week17 Target
[16 empty] | Date | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19
[16 empty] | Daily Target | CR2 TT 1. GTM / Early Pre-sell Order | CR2 TT | CR2 TT End-day | TT Return-Dept | TT Return-Arr | CR2 TT feedback file org. CR2 TT internal review
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week18 Target
[16 empty] | Date | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week19 Target
[16 empty] | Date | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week20 Target
[16 empty] | Date | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week21 Target
[16 empty] | Date | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week22 Target
[16 empty] | Date | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week23 Target
[16 empty] | Date | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30
[16 empty] | Daily Target | CR2 Final Samples Review | CR2 Final Samples Review | 1. CR2 Final Samples XFAC 2. FGT (Finished Goods Testing) Tests & Results > 01/27-03/03 3. GTM/Pre-Sell XFAC | 1. CR2 CBD Upload
1H Target
[16 empty] | 2H Target |  |  | Share CR2 AWB/w BU
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-06
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-02-08 | 2027-02-09 | 2027-02-10 | 2027-02-11 | 2027-02-12 | 2027-02-13
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 2027-02-20
[16 empty] | Daily Target |  |  |  | CR2 FEEDBACK | FINAL LT ADJUST
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-02-22 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-26 | 2027-02-27
[16 empty] | Daily Target | PRE-SELL XFAC
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-06
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13
[16 empty] | Daily Target | GTM SIGN-OFF |  |  |  | SMS ORDER
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 2027-03-21 | 2027-03-22
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-27 | 2027-03-28 | 2027-03-29
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-03-31 | 2027-04-01 | 2027-04-02 | 2027-04-03 | 2027-04-04 | 2027-04-05
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-04-07 | 2027-04-08 | 2027-04-09 | 2027-04-10 | 2027-04-11 | 2027-04-12
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-04-14 | 2027-04-15 | 2027-04-16 | 2027-04-17 | 2027-04-18 | 2027-04-19
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-04-21 | 2027-04-22 | 2027-04-23 | 2027-04-24 | 2027-04-25 | 2027-04-26
[16 empty] | Daily Target | SMS 1 XFAC
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-04-28 | 2027-04-29 | 2027-04-30 | 2027-05-01 | 2027-05-02 | 2027-05-03
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | POST-CR2
Week23 Target
[16 empty] | Date | 2027-05-05 | 2027-05-06 | 2027-05-07 | 2027-05-08 | 2027-05-09 | 2027-05-10
[16 empty] | Daily Target |  | SMS 2 XFAC
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark

## Backup
Product Group (M) | AGE GROUPING | Corporate Marketing Line (M) | Gender (M) | Development Type (M) | Model Name [Short] (M) | Age Group (M) | Model Number (M) | Product Manager (M) | Model Status (M) | Marketing Forecast (M) | Reference Model Number (M) | Outsole Number (M) | Target Material (M) | Technology Concept (M) | Sales Line (M) | Project Calender | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
SHOES | ADULT | LIFESTYLE RUNNING | MALE | TOTALLY NEW | BOOST CUXXION - RAPIDFIT | ADULT | NSS73 | William Hester | RELEASED | 80000 |  | 98345 | TEXTILE | BOOST+ | WALKING RANGE | Week1 Target | 1. Mater Pattern ¦ 2. 1st-Stitched Upper Ready ¦ 3. 1st-File 2D/3D Ready ¦ 4. Stitched Upper 1st-Costing Review/w BU
SHOES | ADULT | LIFESTYLE RUNNING | FEMALE | NEW SILHOUETTE | BOOST CUXXION - RAPIDFIT | ADULT | NSS74 | William Hester | RELEASED | 70000 |  | 98348 | TEXTILE | BOOST+ | WALKING RANGE | Date | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29
SHOES | ADULT | LIFESTYLE RUNNING | MALE | NEW SILHOUETTE | BOOST CUXXION - SOCK | ADULT | NSS75 | William Hester | RELEASED | 75000 |  | 98345 | TEXTILE | BOOST+ | WALKING RANGE | Daily Target | 1. BU shares TP 2. TP Ext. Meeting 3. TP Int. Meeting 4. All Depts. Review TP 5. Master Pattern 6. Collect Issues | 1. BU shares TP 2. TP Ext. Meeting 3. TP Int. Meeting 4. All Depts. Review TP 5. Master Pattern 6. Collect Issues | 1. Receive Upper Mold 2. Cutting Start 3. Treatment Start 4. Costing Ready 5. Remind 2D 1st-File | 1. 2D 1st-File receive 2. BU review 2D 1st-File 3. Review Stitched Upper 4. Make Check list-All stage | 1. 2D 1st-Amend 2. 2D Confirm 3. Start 3D 1st-File | 1. 3D 1st-File receive 2. BU review 3D 1st-File
SHOES | ADULT | LIFESTYLE RUNNING | FEMALE | TAKE DOWN | BOOST CUXXION - SOCK | ADULT | NSS76 | William Hester | RELEASED | 75000 |  | 98348 | TEXTILE | BOOST+ | WALKING RANGE | 1H Target |  | Ext. & Int. Meeting | 1. Master Pattern cross check 2. Review Upper Mold | 1. Follow All stage and Record | 1. 1st Stitched Upper Check List 2. 1st Stitched Upper Impro.
[16 empty] | 2H Target |  | 1. Finish Master Pattern 2. Finish Matl. Collection 3. Finish Matl. Lamination | 1. Cutting process 2. Treatment process | 1. Review Stitched Upper
[16 empty] | Upper Pattern |  | Finish 1st Master Pattern | Review Pattern/w Depts. | 1. Review Stitched Upper 2. Amend Pattern | Amend Pattern | Amend Pattern
[16 empty] | Upper Mold |  | H/O Master Pattern | Finish Upper Mold | 1. Review Stitched Upper 2. Amend Upper Mold | Amend Upper Mold | Amend Upper Mold
[16 empty] | Material WH |  | Collect Materials | Prepare P/O Materials | Prepare P/O Materials | Prepare P/O Materials | Prepare P/O Materials
[16 empty] | Lamination |  | Finish Upper Lamination | Prepare P/O Materials | Prepare P/O Materials | Prepare P/O Materials | Prepare P/O Materials
[16 empty] | Cutting |  | Review TP/Pattern | 1st Cutting
[16 empty] | Treatment |  | Review TP/Pattern | 1st Component Treatment
[16 empty] | Stitching |  | Review TP/Pattern | Review TP/Pattern | 1st Stitching
[16 empty] | Costing |  | Drating Costing Sheet | Costing 1st-File Ready
[16 empty] | Bottom 2D/3D |  | Review TP/Pattern | Work on 2D 1st-File | Review 2D 1st-File/w BU | 1. Confirm 2D 1st-File 2. Work on 3D 1st-File | Review 3D 1st-File/w BU
[16 empty] | Bottom Mold | - | - | -
[16 empty] | Remark | Tech-Pack W/O 1. Day1 with TP 2. HO=Hang Over | 1. Day 2 after TP 2. /w=with 3. P/O=Pull Over | 1. Day 3 | 1. Day 4 2. Impro.=Improvement | 1. Day 5 | 1. Day 6
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week2 Target
[16 empty] | Date | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05
[16 empty] | Daily Target | 1. 3D 1st-Amend | 1. 3D file Confirm | 1. 1st Fast Mold Making | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 1st Remind-H/C | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 1st Remind-H/C | CR0 TT Departure
1H Target
2H Target
[16 empty] | Upper Pattern | Amend Pattern | Amend Pattern | Amend Pattern | Amend Pattern | Finalize Pattern for TT
[16 empty] | Upper Mold | Amend Upper Mold | Amend Upper Mold | Amend Upper Mold | Amend Upper Mold | Finalize Upper Mold for TT
[16 empty] | Material WH | Prepare P/O Materials
[16 empty] | Lamination | Prepare P/O Materials
Cutting
Treatment
Stitching
Costing
[16 empty] | Bottom 2D/3D | Amend 3D 1st-File | Confirm 3D 1st-File
[16 empty] | Bottom Mold |  |  | 1st Fast Mold Review
[16 empty] | Remark | 1. Day 6 | 1. Day 7 | 1. Day 8 | 1. Day 9 2. H/C=Hang-carry | 1. Day 10 | 1. Day 11
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week3 Target
[16 empty] | Date | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12
[16 empty] | Daily Target | CR0 TT Start | CR0 TT | CR0 TT | CR0 TT | CR0 TT | CR0 TT
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week4 Target
[16 empty] | Date | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19
[16 empty] | Daily Target | CR0 TT | CR0 TT | CR0 TT | CR0 TT | CR0 TT | CR0 TT
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week5 Target
[16 empty] | Date | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26
[16 empty] | Daily Target | CR0 TT End-day | TT Return-Dept | TT Return-Arr | CR0 TT feedback file org. CR0 TT internal review
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
[16 empty] | Bottom Mold |  |  |  | 1. Org.=Organize
Remark
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week6 Target
[16 empty] | Date | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | Tech-Pack ¦ 1ST, 2ND, 3RD Pullover ¦ CR0
Week7 Target
[16 empty] | Date | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10
[16 empty] | Daily Target |  |  | 1. Share revised TP 2. Review revised TP 3. 2D/3D 2nd revision | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 2nd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 2nd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 2nd Remind
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week8 Target
[16 empty] | Date | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17
[16 empty] | Daily Target | TT Departure | TT Arrival | 1. CR1 TT Start 2. CR1 2D/3D Sign-off 3. CR1 Tooling Confirmation | 1. CR1 TT 2. Stitched Upper Scan 3. Confirm M/S ETC 4. Confirm O/S ETC | 1. CR1 TT 2. Wooden Pattern ETC | 1. CR1 TT 2. Wooden Pattern ETC
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week9 Target
[16 empty] | Date | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24
[16 empty] | Daily Target | CR1 TT | CR1 TT | CR1 TT End-day | TT Return-Dept | TT Return-Arr | CR1 TT feedback file org. CR1 TT internal review
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week10 Target
[16 empty] | Date | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31
[16 empty] | Daily Target | [5 empty] | 1. China Mold Shop Trip 2. CR1 Molds ETC
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week11 Target
[16 empty] | Date | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07
[16 empty] | Daily Target | 1. China Mold Shop Trip 2. CR1 Molds ETC | 1. China Mold Shop Trip 2. CR1 M/S Component 3. CR1 O/S Component | 1. Trip return-Dept 2. Component hang-carry | 1. Trip return-Arr 2. Component hang-carry | 1. CR1 Assembly 1st-trial | 1. CR1 1st-Sample review
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 4TH, 5TH Pullover ¦ CR1
Week12 Target
[16 empty] | Date | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14
[16 empty] | Daily Target | 1. CR1 Assembly 2nd-trial | 1. CR1 2nd-Sample review | CR1 Final Samples Review | CR1 Final Samples Review | CR1 Final Samples XFAC
1H Target
[16 empty] | 2H Target |  |  |  |  | Share CR1 AWB/w BU
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week13 Target
[16 empty] | Date | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week14 Target
[16 empty] | Date | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week15 Target
[16 empty] | Date | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05
[16 empty] | Daily Target |  |  | 1. Share revised TP 2. Review revised TP 3. 2D/3D 3rd revision | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 3rd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 3rd Remind | 1. Prepare all materials 2. Prepare peronal tools 3. Materials sorting/list 4. Fast Mold 3rd Remind
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week16 Target
[16 empty] | Date | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12
[16 empty] | Daily Target | TT Departure | TT Arrival | CR2 TT Start | CR2 TT | CR2 Tooling Confirmation | CR2 TT
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week17 Target
[16 empty] | Date | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19
[16 empty] | Daily Target | CR2 TT | CR2 TT | CR2 TT End-day | TT Return-Dept | TT Return-Arr | CR2 TT feedback file org. CR2 TT internal review
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week18 Target
[16 empty] | Date | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week19 Target
[16 empty] | Date | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week20 Target
[16 empty] | Date | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week21 Target
[16 empty] | Date | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week22 Target
[16 empty] | Date | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23
Daily Target
1H Target
2H Target
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark
[16 empty] | Stage | 6TH, 7TH Pullover ¦ CR2
Week23 Target
[16 empty] | Date | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30
[16 empty] | Daily Target | CR2 Final Samples Review | CR2 Final Samples Review | CR2 Final Samples XFAC
1H Target
[16 empty] | 2H Target |  |  | Share CR2 AWB/w BU
Upper Pattern
Upper Mold
Material WH
Lamination
Cutting
Treatment
Stitching
Costing
Bottom 2D/3D
Bottom Mold
Remark